## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-5-E TheThinkers
Testing Team Name | fill in when doing cross-team testing
Status | Criteria - as noted by me before, we didn't fully understand this part until sprint 3, so only the last ones are formatted correctly. | Comment
Pass | GIVEN that I am a customer, WHEN I add an item to my order THEN I expect those items to be saved in a cart so I can checkout later, and have more than one items in my order.
Fail - No checkout yet | GIVEN that I am a customer, WHEN I go to checkout THEN I expect to be able to edit (add and delete) items from my cart
Pass | GIVEN that I login to the site as a customer THEN I can access the shopping cart
Pass | GIVEN that I login to the site as ADMIN THEN I can access the admin view (inventory manipulation)
Pass | GIVEN that I am a user WHEN I am logged in THEN I expect to browse the products on the website
Pass | GIVEN that I am logged in as ADMIN THEN I can adjust, add and remove items from the inventory
Pass | Given that I am a user when I use the search bar for a specific item then I expect that item or items that have that phrase I typed.
Sprint 3 - no review yet | Given I am I a customer when I login with a username and then I expect to be able to view the page upon refresh
Sprint 3 - no review yet | Given I am I customer when I login I expect to preserve my login session
Sprint 3 - no review yet | Given I am a customer, when I delete an item from my shopping cart, I expect an item to be deleted and the shopping cart to be refreshed immediately
Sprint 3 - no review yet | Given I am a customer, when I add an item from to shopping cart, I expect an item to be added and the shopping cart to be refreshed immediately
Sprint 3 - no review yet | Given I am a customer, when I access a page with items, I expect to see a way to edit the number of items I interact with (quantity box)
Sprint 3 - not implemented | Given I am a customer when I login then I expect to be able to make a trade in offer
Sprint 3 - not implemented | Given I am a customer when I login then I expect to be able to see the status of my trade-in offers
Sprint 3 - not implemented | Given I am a customer when I login then I expect to be see my current balance
Sprint 3 - not implemented | GIVEN that I have a shopping cart with some items in it. When I click the shopping cart I expect to have the option to checkout.
Sprint 3 - not implemented | Given that I am a customer when on the checout page when I put in my payment method, I expect to recieve my products and lose my money
Sprint 3 - not implemented | GIVEN that I am a customer when click to checkout THEN I expect to see a different view that provides an overview and additional info
Sprint 3 - not implemented | GIVEN that I am a customer when I checkout THEN I expect the inventory stock to be refreshed based on my purchase
Sprint 3 - not implemented | Given that I access the app then I expect a standardized cohesive style across the site
Sprint 3 - not implemented | Given that I access the app then I expect a title to be present on every interactable element
Sprint 3 - not implemented | Given I am the admin when I login then I expect to be able to access trade in offers
Sprint 3 - not implemented | Given I am the admin when I login then I expect to be able to accept incoming trade-in offers
Sprint 3 - not implemented | Given I am the admin when I login then I expect to be able to deny incoming trade-in offers

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
Given that I am on the products page when there are products in the inventory then I see each product and short description.
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.